Teen Quit Program (Phase 1) feasibility pilot –

| Task | Task Completion Date | Outcome of Task | Responsible Party |
| --- | --- | --- | --- |
| - Have Centers self-identify who is interested in participating in the Teen Quit feasibility pilot | January 5, 2023 | Meeting scheduled or TTQ-Teen discussion added to a regularly scheduled network meeting. | Program Offices |
| - Select a minimum of 3 AHECs but up to 12 maximum to participate. Preference will be given to those who have facilitators that have experience working with youth) | January 10, 2023 | Formation of a committee. All participating Centers will agree to meet regularly to oversee the pilot rollout. The committee will appoint someone to coordinate communication among the group and ensure the project moves forward. | Program Office/Center Directors |
| - Obtain a letter from DOH supporting the Teen Quit Program for Centers to use if they choose when approaching the school board. | January 20, 2023 | Letter from DOH in support of the program. | BTFF (Laura Corbin) |
| - Centers piloting the program will draft a program evaluation form to collect information from participants and facilitators | January 20, 2023 | Evaluation forms are ready for a pilot deployment. | Pilot Committee/Center Designate |
| - Centers piloting the program will meet with CHD/Providers for input on approaching schools | February 1, 2023 | Meeting with CHD/Providers from selected counties, report back to committee on progress | Pilot Committee/Center Designate |
| - Participating Centers will approach the schools and/or districts about implementing the program as a trial | February 15, 2023 | Confirmation from districts or schools in the form of an email or MOU (as appropriate). | Pilot Committee/Center Designate |
| - Host TTQ-Teen curriculum review and training. Centers ready to deploy will go over the facilitator’s guide and participant booklet as a group to become familiar with the program. | February 15, 2023 | All pilot facilitators verbalized that they were ready to teach the curriculum. | Pilot Committee |
| - Implement Teen Quit pilot program in at least 3 schools, but up to 10 schools | February – July2023 | Collection of evaluation forms, and discussion of rollout during regular committee meetings. | Pilot Committee |
| - Debrief of Pilot | July 19th, 2023 | A report presented to DOH and Program Offices. | Pilot Committee |
| - Phase 2, implementation discussion | TBA | Meeting scheduled | Program Offices, DOH |